## Overview
TA Recruitment System Requirements Backlog
Workbook contents |  | Role counts |  | Priority counts
All Requirements (Prioritised Backlog) |  | TA | 17 | very high | 15
TA |  | MO | 19 | high | 16
MO |  | Admin | 16 | medium | 14
Admin |  |  |  | low | 6
|  |  |  | very low | 1
Sprint calendar
Sprint | Start | Finish
1 | 2026-03-16 | 2026-03-29
2 | 2026-03-30 | 2026-04-12
3 | 2026-04-13 | 2026-04-26
4 | 2026-04-27 | 2026-05-10
5 | 2026-05-11 | 2026-05-24
Notes | Descriptions follow the 3-line user story format; acceptance criteria are phrased as high-level tests; estimation uses Fibonacci-style story points.

## All Requirements
Role | Story ID | Story Name | Description | Priority | Iteration number | Acceptance Criteria | Estimation (Story Points) | Notes | Date started | Date finished
Admin | AD-01 | Log In as Admin | As an Admin, I want to log in securely, so that I can access system-wide management functions. | very high | 1 | • Verify that an admin can log in with valid credentials. • Verify that invalid admin credentials are rejected. • Verify that successful login opens the admin dashboard. | 2 | Prerequisite for all admin functions. | 2026-03-16 | 2026-03-18
Admin | AD-11 | Reset Admin Password | As an Admin, I want to reset my password using a secure recovery process, so that I can regain access if I forget it. | very high | 1 | • Admin can initiate password reset via email link. • System generates a time-limited reset token. • New password must meet complexity. • Password is updated and logged securely. | 3 | Should integrate with university email service. | 2026-05-15 | 2026-05-22
MO | MO-01 | Log In as Organiser | As a Module Organiser (MO), I want to log in to the system, so that I can manage postings and applicants for my module. | very high | 1 | • Verify that a module organiser can log in with valid credentials. • Verify that invalid credentials generate an error message. • Verify that successful login opens the organiser dashboard. | 2 | Prerequisite for all MO-facing features. | 2026-03-16 | 2026-03-18
MO | MO-02 | Create Job Posting | As a Module Organiser (MO), I want to create a job posting, so that I can advertise teaching assistant opportunities for my course. | very high | 1 | • Verify that a module organiser can create a job posting with title, description, requirements, and deadline. • Verify that required fields must be completed before saving. • Verify that a saved job is stored in the system as a draft or open posting. | 5 | Core recruitment capability. | 2026-03-17 | 2026-03-22
MO | MO-03 | Publish Job Posting | As a Module Organiser (MO), I want to publish a job posting, so that eligible TAs can view and apply for it. | very high | 1 | • Verify that a created job posting can be published. • Verify that a published posting becomes visible to eligible TAs. • Verify that unpublished postings remain hidden from TA users. | 3 | Depends on MO-02. | 2026-03-20 | 2026-03-24
TA | TA-01 | Register Account | As a Teaching Assistant (TA), I want to register an account, so that I can access the recruitment system with my university email. | very high | 1 | • Verify that a TA can register using a valid university email address. • Verify that required fields are validated before account creation. • Verify that a successful registration enables the TA to log in. | 3 | Prerequisite for all TA-facing features. | 2026-03-16 | 2026-03-18
TA | TA-02 | Log In to System | As a Teaching Assistant (TA), I want to log in to the system, so that I can manage my profile and job applications securely. | very high | 1 | • Verify that valid credentials allow the TA to access the system. • Verify that invalid credentials display an error message. • Verify that the TA is redirected to the correct landing page after login. | 2 | Core access feature for TA users. | 2026-03-16 | 2026-03-19
TA | TA-03 | Create Applicant Profile | As a Teaching Assistant (TA), I want to create my applicant profile, so that employers can understand my background, skills, and availability. | very high | 1 | • Verify that the TA can create a profile with name, student ID, skills, and availability. • Verify that mandatory profile fields cannot be left blank. • Verify that the saved profile can be viewed after submission. | 5 | Required before a TA can apply for jobs. | 2026-03-17 | 2026-03-22
TA | TA-04 | Edit Applicant Profile | As a Teaching Assistant (TA), I want to edit my applicant profile, so that my information stays accurate and up to date. | high | 1 | • Verify that an existing profile can be edited. • Verify that updated profile information is saved successfully. • Verify that the latest profile details are displayed when the page is reopened. | 3 | Depends on TA-03. | 2026-03-20 | 2026-03-24
TA | TA-05 | Upload CV | As a Teaching Assistant (TA), I want to upload my CV, so that module organisers can review my qualifications during recruitment. | very high | 1 | • Verify that the TA can upload a CV in an allowed file format. • Verify that an invalid file type is rejected with a clear message. • Verify that the uploaded CV is visible to authorised module organisers. | 3 | Depends on TA-03. | 2026-03-21 | 2026-03-25
Admin | AD-12 | View Login Activity | As an Admin, I want to view login history and failed attempts, so that I can monitor system security. | high | 2 | • Admin can access a dashboard showing recent logins by role. • Failed login attempts are logged with timestamp and IP. • Ability to filter logs by date/role. | 5 | Useful for auditing and detecting suspicious activity. | 2026-05-11 | 2026-05-17
MO | MO-04 | Edit Job Posting | As a Module Organiser (MO), I want to edit a job posting, so that I can keep role details accurate throughout recruitment. | high | 2 | • Verify that a module organiser can edit job details after creation. • Verify that updated details are saved without losing linked applications. • Verify that the revised job information is shown to users after the update. | 3 | Depends on MO-02. | 2026-03-30 | 2026-04-03
MO | MO-05 | Close Job Posting | As a Module Organiser (MO), I want to close a job posting, so that applications stop when the deadline is reached or places are filled. | high | 2 | • Verify that a module organiser can close an active job posting. • Verify that closed jobs no longer accept new applications. • Verify that existing application records remain available for review after closure. | 3 | Supports job lifecycle management. | 2026-04-01 | 2026-04-05
MO | MO-06 | View Applicants for a Job | As a Module Organiser (MO), I want to view applicants for a job, so that I can review who has applied for my vacancy. | very high | 2 | • Verify that a module organiser can view all applicants linked to a specific job. • Verify that each applicant entry shows relevant profile and CV information. • Verify that applicants are displayed against the correct vacancy. | 5 | Core screening feature. | 2026-04-03 | 2026-04-08
MO | MO-11 | Manage My Module Access | As a Module Organiser, I want to restrict access to my module’s job postings to specific TAs, so that only authorized applicants can apply. | high | 2 | • MO can select which TAs are allowed to apply to their module. • System enforces access restriction during application submission. • MO can view list of authorized TAs. | 4 | May require integration with user groups or roles. | 2026-04-13 | 2026-04-18
MO | MO-13 | Preview Job Posting | As a Module Organiser (MO), I want to preview the job posting from a TA’s perspective before publishing, so that I can ensure the layout and information are accurate. | Medium | 2 | • Verify that the MO can click a "Preview" button while in "Draft" status to view the full display page as seen by TAs. • Verify that entering preview mode does not change the job status (it remains "Draft"). • Verify that the preview interface is visually identical to the TA's application view but disables the submission functionality. | 2 | UX improvement to prevent formatting errors in public postings. | 2026-03-30 | 2026-04-12
MO | MO-15 | View Job Posting Dashboard | As a Module Organiser (MO), I want to view all my job postings and their statuses in a centralized dashboard, so that I can efficiently manage recruitment progress across multiple modules. | High | 2 | • Verify that the "My Jobs" page displays all jobs belonging to the logged-in MO, showing Title, Status, Deadline, and Applicant Count. • Verify that the MO can filter the list by status (Draft, Open, Closed). • Verify that quick-action links (Edit, Publish, Close, View Applicants) are accessible directly from the dashboard list. | 5 | Core navigation hub for MOs to manage their recruitment pipeline. | 2026-03-30 | 2026-04-12
TA | TA-06 | Browse Available Jobs | As a Teaching Assistant (TA), I want to browse available jobs, so that I can identify roles that match my interests and schedule. | very high | 2 | • Verify that all open positions are displayed to the TA. • Verify that each job listing shows key information such as title, module, deadline, and workload. • Verify that closed positions are not shown in the default results. | 5 | Depends on published job postings. | 2026-03-30 | 2026-04-04
TA | TA-07 | Search and Filter Jobs | As a Teaching Assistant (TA), I want to search and filter jobs, so that I can find suitable opportunities more efficiently. | high | 2 | • Verify that jobs can be searched by keyword. • Verify that results can be filtered by module, time slot, or workload. • Verify that filtered results update correctly when search conditions change. | 5 | Improves job discovery efficiency. | 2026-04-01 | 2026-04-06
TA | TA-08 | Apply for a Job | As a Teaching Assistant (TA), I want to apply for a job, so that I can be considered for teaching assistant work. | very high | 2 | • Verify that only eligible TAs with completed profile details can submit an application. • Verify that a successful application creates a new application record. • Verify that the system prevents duplicate applications for the same job. | 8 | Core TA workflow. | 2026-04-03 | 2026-04-09
TA | TA-09 | Track Application Status | As a Teaching Assistant (TA), I want to track my application status, so that I know the progress and outcome of each application. | high | 2 | • Verify that the TA can view the status of every submitted application. • Verify that statuses such as Submitted, Under Review, Accepted, and Rejected are displayed correctly. • Verify that status changes are reflected without altering the original application record. | 3 | Depends on TA-08 and MO decisions. | 2026-04-06 | 2026-04-10
TA | TA-11 | Update Personal Profile | As a Teaching Assistant (TA), I want to edit my profile information after registration, so that my details remain accurate. | medium | 2 | • TA can update name, contact info, and bio. • Changes are saved to the user profile text file.3. System logs last updated timestamp. | 2 | Ensure data consistency with initial registration. | 2026-04-13 | 2026-04-18
TA | TA-15 | View Application History | As a Teaching Assistant(TA), I want to view my past applications, so that I can track my previous job attempts and outcomes. | medium | 2 | • Verify that all submitted applications are listed. • Verify that each record displays job title, submission date, and status. • Verify that the list includes both active and closed applications. | 5 | Helps maintain transparency. | 2026-04-16 | 2026-04-20
TA | TA-16 | Update Availability | As a Teaching Assistant(TA), I want to update my weekly availability,, so that module organisers can assign work based on my schedule. | medium | 2 | • Verify that the TA can update available time slots. • Verify that changes are saved correctly. • Verify that updated availability appears in the profile view. | 8 | Extends TA-03 profile information | 2026-04-20 | 2026-05-02
Admin | AD-06 | View All Job Postings | As an Admin, I want to view all job postings, so that I can oversee recruitment activity across the whole system. | medium | 3 | • Verify that the admin can view all job postings created by module organisers. • Verify that each posting shows owner, module, deadline, and status. • Verify that the list includes both open and closed postings. | 3 | Supports oversight of recruitment activity. | 2026-04-13 | 2026-04-17
MO | MO-07 | Filter Applicants | As a Module Organiser (MO), I want to filter applicants, so that I can identify the most suitable candidates more quickly. | high | 3 | • Verify that applicants can be filtered by skills, availability, or experience. • Verify that the filtered list only shows matching candidates. • Verify that the organiser can reset the filters and return to the full list. | 5 | Improves screening efficiency. | 2026-04-13 | 2026-04-18
MO | MO-08 | Shortlist Applicants | As a Module Organiser (MO), I want to shortlist applicants, so that I can narrow down promising candidates for final selection. | high | 3 | • Verify that a module organiser can mark an applicant as shortlisted. • Verify that shortlisted applicants appear in a shortlist view. • Verify that the updated shortlist status is visible to the TA where appropriate. | 3 | Depends on MO-06. | 2026-04-15 | 2026-04-19
MO | MO-09 | Accept or Reject Applicants | As a Module Organiser (MO), I want to accept or reject applicants, so that I can complete hiring decisions for each vacancy. | very high | 3 | • Verify that a module organiser can record a final decision as accepted or rejected. • Verify that the system warns the organiser when available positions are already filled. • Verify that the final decision is reflected in the TA application status. | 8 | Core hiring decision feature. | 2026-04-16 | 2026-04-24
MO | MO-12 | Clone/Template Job Posting | As a Module Organiser , I want to clone a previous job posting as a template, so that I can quickly create similar postings for new semesters. | Low | 3 | • Verify that the system provides a "Clone" button that pre-fills all fields except for the dates. • Verify that the newly cloned job is set to "Draft" status by default. • Verify that any modifications to the cloned copy do not affect the data of the original posting. | 3 | Efficiency feature to reduce repetitive data entry for recurring modules. | 2026-04-13 | 2026-04-26
MO | MO-14 | Withdraw/Cancel Posting | As a Module Organiser (MO), I want to withdraw a published job posting if requirements change, so that I can inform existing applicants and stop new ones. | Medium | 3 | • Verify that the MO can withdraw or cancel a job that is currently "Open". • Verify that the system automatically updates the status of all associated applications to "Job Cancelled". • Verify that a confirmation prompt appears before withdrawal to prevent accidental cancellation. | 5 | Includes logic for batch-updating application records in the text-based files. | 2026-04-13 | 2026-04-26
TA | TA-10 | Receive Notification of Outcome | As a Teaching Assistant (TA), I want to receive notifications when my application status changes, so that I do not miss important updates. | medium | 3 | • Verify that the TA receives a notification when an application status changes. • Verify that unread notifications are clearly highlighted. • Verify that the TA can open a notification to review the latest update. | 5 | Can be extended to email notifications later. | 2026-04-13 | 2026-04-18
TA | TA-12 | Request Role Upgrade | As a Teaching Assistant(TA), I want to request elevated permissions (e.g., to apply for multiple modules), so that I can express interest in broader opportunities. | low | 3 | • TA can submit a request form explaining desired role change. • Request is routed to Admin for approval. • Admin receives notification and can approve/deny. • Status is visible to TA. | 5 | Optional feature; useful for scalability. | 2026-04-14 | 2026-04-19
TA | TA-13 | View Job Details | As a Teaching Assistant(TA), I want to view detailed information about a job posting, so that I can decide whether the position is suitable before applying. | high | 3 | • Verify that the TA can open a job listing to view detailed information. • Verify that details include module name, responsibilities, workload, and deadline. • Verify that the page clearly shows whether the job is still open | 5 | Extends TA-06 browsing feature. | 2026-04-14 | 2026-04-19
TA | TA-14 | Withdraw Job Application | As a Teaching Assistant(TA), I want to withdraw a submitted job application, so that I can correct mistakes or change my decision. | medium | 3 | • Verify that a TA can withdraw an application before it is reviewed • Verify that the application status changes to “Withdrawn”. • Verify that withdrawn applications cannot be reconsidered unless reapplied. | 5 | Depends on TA-08. | 2026-04-15 | 2026-04-20
TA | TA-17 | Log Out of System | As a Teaching Assistant(TA), I want to log out of the system, so that my account remains secure when I finish using the platform. | high | 3 | • Verify that the TA can log out successfully. • Verify that the session ends immediately after logout. • Verify that the TA must log in again to access protected pages. | 8 | Basic security feature. | 2026-05-02 | 2026-05-15
Admin | AD-02 | View All TA Workloads | As an Admin, I want to view all TA workloads, so that I can monitor teaching allocation across modules. | very high | 4 | • Verify that the admin can view TA workload information across modules. • Verify that workload totals are based on accepted or assigned jobs. • Verify that workload data is displayed per TA in a readable format. | 5 | Core monitoring requirement. | 2026-04-27 | 2026-05-03
Admin | AD-03 | Filter Workload by Term or Module | As an Admin, I want to filter workload data by term or module, so that I can analyse staffing patterns more effectively. | high | 4 | • Verify that workload data can be filtered by term, module, or department. • Verify that filtered results update correctly. • Verify that clearing the filters restores the complete dataset. | 3 | Depends on AD-02. | 2026-04-28 | 2026-05-04
Admin | AD-04 | Detect Overloaded TAs | As an Admin, I want to detect overloaded TAs, so that I can identify unfair or excessive workload assignments. | very high | 4 | • Verify that the system flags TAs whose workload exceeds the configured threshold. • Verify that the admin can view the list of overloaded TAs. • Verify that the threshold used for overload checking can be configured by an authorised user. | 5 | Supports workload fairness checks. | 2026-04-29 | 2026-05-06
Admin | AD-05 | View Hiring Distribution | As an Admin, I want to view hiring distribution, so that I can check whether opportunities are allocated fairly among TAs. | high | 4 | • Verify that the admin can view how opportunities are distributed across TAs. • Verify that the view highlights both under-assigned and heavily assigned TAs. • Verify that the distribution data is consistent with the hiring records. | 5 | Supports allocation fairness analysis. | 2026-05-01 | 2026-05-07
Admin | AD-07 | View Application Statistics | As an Admin, I want to view application statistics, so that I can evaluate overall recruitment performance. | medium | 4 | • Verify that the admin can view total applications, acceptances, and rejections. • Verify that the statistics are calculated from the current system data. • Verify that the displayed totals remain consistent across the reporting views. | 3 | Supports management reporting. | 2026-05-02 | 2026-05-08
Admin | AD-13 | Export Workload Report | As an Admin, I want to export workload data to a CSV file, so that I can share it with other administrators or use it for offline analysis. | medium | 4 | • Verify that a button or link is available to export the current workload view (or all workload data). • Verify that the exported file is in CSV format and contains all relevant fields (TA name, modules, total hours, etc.). • Verify that special characters and line breaks are handled correctly in the export. | 3 | Depends on AD-02; useful for reporting | 2026-05-01 | 2026-05-07
Admin | AD-14 | Configure Workload Threshold | As an Admin, I want to configure the workload threshold (maximum allowed hours) for TAs, so that overload detection can be customised per semester. | high | 4 | • Verify that the admin can access a configuration page to set the threshold value. • Verify that the threshold is saved and used by the overload detection feature (AD-04). • Verify that only authorised admins can modify the threshold. | 3 | Supports flexible fairness rules | 2026-05-02 | 2026-05-08
Admin | AD-15 | View Workload History | As an Admin, I want to view historical workload data for each TA across past terms, so that I can analyse long-term allocation patterns. | low | 4 | • Verify that the admin can select a past term and see workload data as it was at that time (or aggregated). • Verify that the historical view includes the same metrics as the current view (modules, hours, status). • Verify that data is correctly archived or recomputed from historical records. | 5 | Requires storing snapshots or querying past assignments | 2026-05-11 | 2026-05-17
Admin | AD-16 | View Allocation Fairness Index | As an Admin, I want to see a fairness index (e.g., Gini coefficient or simple distribution chart) of TA workloads, so that I can quickly assess whether assignments are balanced. | low | 4 | • Verify that a visual representation (e.g., bar chart or pie chart) shows the distribution of workload among TAs. • Verify that a numeric fairness metric (if feasible) is displayed. • Verify that the view updates when filters (term/module) are applied. | 5 | May require statistical calculation; consider using simple percentages | 2026-05-07 | 2026-05-13
MO | MO-10 | View Recruitment Summary | As a Module Organiser (MO), I want to view recruitment summary statistics, so that I can monitor the progress of hiring for a job. | medium | 4 | • Verify that recruitment summary statistics show the total number of applicants. • Verify that the summary distinguishes pending, accepted, and rejected applications. • Verify that summary totals match the underlying application data. | 3 | Useful for quick recruitment monitoring. | 2026-04-27 | 2026-05-01
MO | MO-16 | Add Internal Evaluation Notes | As a Module Organiser (MO), I want to add internal evaluation notes, so that I can record my assessment and refer to it during the selection process. | Medium | 4 | • Verify that the MO can enter text notes on an applicant's profile. • Verify that these notes are only visible to MOs and Admins. • Verify that notes are saved and remain accessible for future review. | 3 | Helps track subjective feedback. | 2026-04-27 | 2026-05-01
MO | MO-17 | Applicant Rating System | As a Module Organiser (MO), I want to rate applicants using a scoring system, so that I can compare candidates objectively based on set criteria. | Medium | 4 | • Verify that the MO can assign a numeric score (e.g., 1-5) to candidates. • Verify that the system calculates and displays the average score per candidate. • Verify that applicants can be sorted by their rating. | 5 | Enables objective ranking of candidates. | 2026-04-28 | 2026-05-03
MO | MO-18 | Bulk Reject Applications | As a Module Organiser (MO), I want to bulk reject applications, so that I can efficiently manage a high volume of candidates. | Medium | 4 | • Verify that the MO can select multiple candidates for rejection at once. • Verify that a confirmation prompt appears before finalizing the bulk action. • Verify that the status of all selected candidates is updated to 'Rejected'. | 3 | Increases efficiency during peak cycles. | 2026-04-29 | 2026-05-04
Admin | AD-08 | Manage User Accounts | As an Admin, I want to manage user accounts, so that I can control access and maintain system integrity. | high | 5 | • Verify that the admin can activate, suspend, or deactivate user accounts. • Verify that suspended or deactivated users cannot log in. • Verify that account status changes are saved immediately. | 5 | Supports system governance. | 2026-05-11 | 2026-05-17
Admin | AD-09 | Generate Management Report | As an Admin, I want to generate management reports, so that I can support review and decision-making at school level. | low | 5 | • Verify that the admin can export management reports in a supported format. • Verify that exported reports match the data shown on screen. • Verify that generated files can be downloaded successfully. | 5 | Management-facing enhancement. | 2026-05-13 | 2026-05-20
Admin | AD-10 | View Audit Log | As an Admin, I want to view the audit log, so that I can trace important actions taken in the system. | very low | 5 | • Verify that the admin can view audit log entries for key system actions. • Verify that each log entry shows the action, user, and timestamp. • Verify that audit log entries are read-only. | 3 | Audit and traceability enhancement. | 2026-05-15 | 2026-05-22
MO | MO-19 | Automated Eligibility Filtering | As a Module Organiser (MO), I want to set automated filtering rules, so that I can quickly identify applicants who do not meet mandatory requirements. | Low | 5 | • Verify that the MO can define filters based on GPA or specific profile fields. • Verify that applicants failing the filter are automatically moved to an 'Ineligible' list. • Verify that the MO can manually override or review filtered applicants. | 5 | Reduces manual screening time. | 2026-05-01 | 2026-05-06

## TA
Story ID | Story Name | Description | Priority | Iteration number | Acceptance Criteria | Estimation (Story Points) | Notes | Date started | Date finished
TA-01 | Register Account | As a Teaching Assistant (TA), I want to register an account, so that I can access the recruitment system with my university email. | very high | 1 | • Verify that a TA can register using a valid university email address. • Verify that required fields are validated before account creation. • Verify that a successful registration enables the TA to log in. | 3 | Prerequisite for all TA-facing features. | 2026-03-16 | 2026-03-18
TA-02 | Log In to System | As a Teaching Assistant (TA), I want to log in to the system, so that I can manage my profile and job applications securely. | very high | 1 | • Verify that valid credentials allow the TA to access the system. • Verify that invalid credentials display an error message. • Verify that the TA is redirected to the correct landing page after login. | 2 | Core access feature for TA users. | 2026-03-16 | 2026-03-19
TA-03 | Create Applicant Profile | As a Teaching Assistant (TA), I want to create my applicant profile, so that employers can understand my background, skills, and availability. | very high | 1 | • Verify that the TA can create a profile with name, student ID, skills, and availability. • Verify that mandatory profile fields cannot be left blank. • Verify that the saved profile can be viewed after submission. | 5 | Required before a TA can apply for jobs. | 2026-03-17 | 2026-03-22
TA-04 | Edit Applicant Profile | As a Teaching Assistant (TA), I want to edit my applicant profile, so that my information stays accurate and up to date. | high | 1 | • Verify that an existing profile can be edited. • Verify that updated profile information is saved successfully. • Verify that the latest profile details are displayed when the page is reopened. | 3 | Depends on TA-03. | 2026-03-20 | 2026-03-24
TA-05 | Upload CV | As a Teaching Assistant (TA), I want to upload my CV, so that module organisers can review my qualifications during recruitment. | very high | 1 | • Verify that the TA can upload a CV in an allowed file format. • Verify that an invalid file type is rejected with a clear message. • Verify that the uploaded CV is visible to authorised module organisers. | 3 | Depends on TA-03. | 2026-03-21 | 2026-03-25
TA-06 | Browse Available Jobs | As a Teaching Assistant (TA), I want to browse available jobs, so that I can identify roles that match my interests and schedule. | very high | 2 | • Verify that all open positions are displayed to the TA. • Verify that each job listing shows key information such as title, module, deadline, and workload. • Verify that closed positions are not shown in the default results. | 5 | Depends on published job postings. | 2026-03-30 | 2026-04-04
TA-07 | Search and Filter Jobs | As a Teaching Assistant (TA), I want to search and filter jobs, so that I can find suitable opportunities more efficiently. | high | 2 | • Verify that jobs can be searched by keyword. • Verify that results can be filtered by module, time slot, or workload. • Verify that filtered results update correctly when search conditions change. | 5 | Improves job discovery efficiency. | 2026-04-01 | 2026-04-06
TA-08 | Apply for a Job | As a Teaching Assistant (TA), I want to apply for a job, so that I can be considered for teaching assistant work. | very high | 2 | • Verify that only eligible TAs with completed profile details can submit an application. • Verify that a successful application creates a new application record. • Verify that the system prevents duplicate applications for the same job. | 8 | Core TA workflow. | 2026-04-03 | 2026-04-09
TA-09 | Track Application Status | As a Teaching Assistant (TA), I want to track my application status, so that I know the progress and outcome of each application. | high | 2 | • Verify that the TA can view the status of every submitted application. • Verify that statuses such as Submitted, Under Review, Accepted, and Rejected are displayed correctly. • Verify that status changes are reflected without altering the original application record. | 3 | Depends on TA-08 and MO decisions. | 2026-04-06 | 2026-04-10
TA-10 | Receive Notification of Outcome | As a Teaching Assistant (TA), I want to receive notifications when my application status changes, so that I do not miss important updates. | medium | 3 | • Verify that the TA receives a notification when an application status changes. • Verify that unread notifications are clearly highlighted. • Verify that the TA can open a notification to review the latest update. | 5 | Can be extended to email notifications later. | 2026-04-13 | 2026-04-18
TA-11 | Update Personal Profile | As a Teaching Assistant (TA), I want to edit my profile information after registration, so that my details remain accurate. | medium | 2 | • TA can update name, contact info, and bio. • Changes are saved to the user profile text file.3. System logs last updated timestamp. | 2 | Ensure data consistency with initial registration. | 2026-04-13 | 2026-04-18
TA-12 | Request Role Upgrade | As a Teaching Assistant(TA), I want to request elevated permissions (e.g., to apply for multiple modules), so that I can express interest in broader opportunities. | low | 3 | • TA can submit a request form explaining desired role change. • Request is routed to Admin for approval. • Admin receives notification and can approve/deny. • Status is visible to TA. | 5 | Optional feature; useful for scalability. | 2026-04-14 | 2026-04-19
TA-13 | View Job Details | As a Teaching Assistant(TA), I want to view detailed information about a job posting, so that I can decide whether the position is suitable before applying. | high | 3 | • Verify that the TA can open a job listing to view detailed information. • Verify that details include module name, responsibilities, workload, and deadline. • Verify that the page clearly shows whether the job is still open | 5 | Extends TA-06 browsing feature. | 2026-04-14 | 2026-04-19
TA-14 | Withdraw Job Application | As a Teaching Assistant(TA), I want to withdraw a submitted job application, so that I can correct mistakes or change my decision. | medium | 3 | • Verify that a TA can withdraw an application before it is reviewed • Verify that the application status changes to “Withdrawn”. • Verify that withdrawn applications cannot be reconsidered unless reapplied. | 5 | Depends on TA-08. | 2026-04-15 | 2026-04-20
TA-15 | View Application History | As a Teaching Assistant(TA), I want to view my past applications, so that I can track my previous job attempts and outcomes. | medium | 2 | • Verify that all submitted applications are listed. • Verify that each record displays job title, submission date, and status. • Verify that the list includes both active and closed applications. | 5 | Helps maintain transparency. | 2026-04-16 | 2026-04-20
TA-16 | Update Availability | As a Teaching Assistant(TA), I want to update my weekly availability,, so that module organisers can assign work based on my schedule. | medium | 2 | • Verify that the TA can update available time slots. • Verify that changes are saved correctly. • Verify that updated availability appears in the profile view. | 8 | Extends TA-03 profile information | 2026-04-20 | 2026-05-02
TA-17 | Log Out of System | As a Teaching Assistant(TA), I want to log out of the system, so that my account remains secure when I finish using the platform. | high | 3 | • Verify that the TA can log out successfully. • Verify that the session ends immediately after logout. • Verify that the TA must log in again to access protected pages. | 8 | Basic security feature. | 2026-05-02 | 2026-05-15

## MO
Story ID | Story Name | Description | Priority | Iteration number | Acceptance Criteria | Estimation (Story Points) | Notes | Date started | Date finished
MO-01 | Log In as Organiser | As a Module Organiser (MO), I want to log in to the system, so that I can manage postings and applicants for my module. | very high | 1 | • Verify that a module organiser can log in with valid credentials. • Verify that invalid credentials generate an error message. • Verify that successful login opens the organiser dashboard. | 2 | Prerequisite for all MO-facing features. | 2026-03-16 | 2026-03-18
MO-02 | Create Job Posting | As a Module Organiser (MO), I want to create a job posting, so that I can advertise teaching assistant opportunities for my course. | very high | 1 | • Verify that a module organiser can create a job posting with title, description, requirements, and deadline. • Verify that required fields must be completed before saving. • Verify that a saved job is stored in the system as a draft or open posting. | 5 | Core recruitment capability. | 2026-03-17 | 2026-03-22
MO-03 | Publish Job Posting | As a Module Organiser (MO), I want to publish a job posting, so that eligible TAs can view and apply for it. | very high | 1 | • Verify that a created job posting can be published. • Verify that a published posting becomes visible to eligible TAs. • Verify that unpublished postings remain hidden from TA users. | 3 | Depends on MO-02. | 2026-03-20 | 2026-03-24
MO-04 | Edit Job Posting | As a Module Organiser (MO), I want to edit a job posting, so that I can keep role details accurate throughout recruitment. | high | 2 | • Verify that a module organiser can edit job details after creation. • Verify that updated details are saved without losing linked applications. • Verify that the revised job information is shown to users after the update. | 3 | Depends on MO-02. | 2026-03-30 | 2026-04-03
MO-05 | Close Job Posting | As a Module Organiser (MO), I want to close a job posting, so that applications stop when the deadline is reached or places are filled. | high | 2 | • Verify that a module organiser can close an active job posting. • Verify that closed jobs no longer accept new applications. • Verify that existing application records remain available for review after closure. | 3 | Supports job lifecycle management. | 2026-04-01 | 2026-04-05
MO-06 | View Applicants for a Job | As a Module Organiser (MO), I want to view applicants for a job, so that I can review who has applied for my vacancy. | very high | 2 | • Verify that a module organiser can view all applicants linked to a specific job. • Verify that each applicant entry shows relevant profile and CV information. • Verify that applicants are displayed against the correct vacancy. | 5 | Core screening feature. | 2026-04-03 | 2026-04-08
MO-07 | Filter Applicants | As a Module Organiser (MO), I want to filter applicants, so that I can identify the most suitable candidates more quickly. | high | 3 | • Verify that applicants can be filtered by skills, availability, or experience. • Verify that the filtered list only shows matching candidates. • Verify that the organiser can reset the filters and return to the full list. | 5 | Improves screening efficiency. | 2026-04-13 | 2026-04-18
MO-08 | Shortlist Applicants | As a Module Organiser (MO), I want to shortlist applicants, so that I can narrow down promising candidates for final selection. | high | 3 | • Verify that a module organiser can mark an applicant as shortlisted. • Verify that shortlisted applicants appear in a shortlist view. • Verify that the updated shortlist status is visible to the TA where appropriate. | 3 | Depends on MO-06. | 2026-04-15 | 2026-04-19
MO-09 | Accept or Reject Applicants | As a Module Organiser (MO), I want to accept or reject applicants, so that I can complete hiring decisions for each vacancy. | very high | 3 | • Verify that a module organiser can record a final decision as accepted or rejected. • Verify that the system warns the organiser when available positions are already filled. • Verify that the final decision is reflected in the TA application status. | 8 | Core hiring decision feature. | 2026-04-16 | 2026-04-24
MO-10 | View Recruitment Summary | As a Module Organiser (MO), I want to view recruitment summary statistics, so that I can monitor the progress of hiring for a job. | medium | 4 | • Verify that recruitment summary statistics show the total number of applicants. • Verify that the summary distinguishes pending, accepted, and rejected applications. • Verify that summary totals match the underlying application data. | 3 | Useful for quick recruitment monitoring. | 2026-04-27 | 2026-05-01
MO-11 | Manage My Module Access | As a Module Organiser, I want to restrict access to my module’s job postings to specific TAs, so that only authorized applicants can apply. | high | 2 | • MO can select which TAs are allowed to apply to their module. • System enforces access restriction during application submission. • MO can view list of authorized TAs. | 4 | May require integration with user groups or roles. | 2026-04-13 | 2026-04-18
MO-12 | Clone/Template Job Posting | As a Module Organiser , I want to clone a previous job posting as a template, so that I can quickly create similar postings for new semesters. | Low | 3 | • Verify that the system provides a "Clone" button that pre-fills all fields except for the dates. • Verify that the newly cloned job is set to "Draft" status by default. • Verify that any modifications to the cloned copy do not affect the data of the original posting. | 3 | Efficiency feature to reduce repetitive data entry for recurring modules. | 2026-04-13 | 2026-04-26
MO-13 | Preview Job Posting | As a Module Organiser (MO), I want to preview the job posting from a TA’s perspective before publishing, so that I can ensure the layout and information are accurate. | Medium | 2 | • Verify that the MO can click a "Preview" button while in "Draft" status to view the full display page as seen by TAs. • Verify that entering preview mode does not change the job status (it remains "Draft"). • Verify that the preview interface is visually identical to the TA's application view but disables the submission functionality. | 2 | UX improvement to prevent formatting errors in public postings. | 2026-03-30 | 2026-04-12
MO-14 | Withdraw/Cancel Posting | As a Module Organiser (MO), I want to withdraw a published job posting if requirements change, so that I can inform existing applicants and stop new ones. | Medium | 3 | • Verify that the MO can withdraw or cancel a job that is currently "Open". • Verify that the system automatically updates the status of all associated applications to "Job Cancelled". • Verify that a confirmation prompt appears before withdrawal to prevent accidental cancellation. | 5 | Includes logic for batch-updating application records in the text-based files. | 2026-04-13 | 2026-04-26
MO-15 | View Job Posting Dashboard | As a Module Organiser (MO), I want to view all my job postings and their statuses in a centralized dashboard, so that I can efficiently manage recruitment progress across multiple modules. | High | 2 | • Verify that the "My Jobs" page displays all jobs belonging to the logged-in MO, showing Title, Status, Deadline, and Applicant Count. • Verify that the MO can filter the list by status (Draft, Open, Closed). • Verify that quick-action links (Edit, Publish, Close, View Applicants) are accessible directly from the dashboard list. | 5 | Core navigation hub for MOs to manage their recruitment pipeline. | 2026-03-30 | 2026-04-12
MO-16 | Add Internal Evaluation Notes | As a Module Organiser (MO), I want to add internal evaluation notes, so that I can record my assessment and refer to it during the selection process. | Medium | 4 | • Verify that the MO can enter text notes on an applicant's profile. • Verify that these notes are only visible to MOs and Admins. • Verify that notes are saved and remain accessible for future review." | 3 | Helps track subjective feedback. | 2026-04-27 | 2026-05-01
MO-17 | Applicant Rating System | As a Module Organiser (MO), I want to rate applicants using a scoring system, so that I can compare candidates objectively based on set criteria. | Medium | 4 | • Verify that the MO can assign a numeric score (e.g., 1-5) to candidates. • Verify that the system calculates and displays the average score per candidate. • Verify that applicants can be sorted by their rating. | 5 | Enables objective ranking of candidates. | 2026-04-28 | 2026-05-03
MO-18 | Bulk Reject Applications | As a Module Organiser (MO), I want to bulk reject applications, so that I can efficiently manage a high volume of candidates." | Medium | 4 | • Verify that the MO can select multiple candidates for rejection at once. • Verify that a confirmation prompt appears before finalizing the bulk action. • Verify that the status of all selected candidates is updated to 'Rejected'. | 3 | Increases efficiency during peak cycles. | 2026-04-29 | 2026-05-04
MO-19 | Automated Eligibility Filtering | As a Module Organiser (MO), I want to set automated filtering rules, so that I can quickly identify applicants who do not meet mandatory requirements. | Low | 5 | • Verify that the MO can define filters based on GPA or specific profile fields. • Verify that applicants failing the filter are automatically moved to an 'Ineligible' list. • Verify that the MO can manually override or review filtered applicants. | 5 | Reduces manual screening time. | 2026-05-01 | 2026-05-06

## Admin
Story ID | Story Name | Description | Priority | Iteration number | Acceptance Criteria | Estimation (Story Points) | Notes | Date started | Date finished
AD-01 | Log In as Admin | As an Admin, I want to log in securely, so that I can access system-wide management functions. | very high | 1 | • Verify that an admin can log in with valid credentials. • Verify that invalid admin credentials are rejected. • Verify that successful login opens the admin dashboard. | 2 | Prerequisite for all admin functions. | 2026-03-16 | 2026-03-18
AD-02 | View All TA Workloads | As an Admin, I want to view all TA workloads, so that I can monitor teaching allocation across modules. | very high | 4 | • Verify that the admin can view TA workload information across modules. • Verify that workload totals are based on accepted or assigned jobs. • Verify that workload data is displayed per TA in a readable format. | 5 | Core monitoring requirement. | 2026-04-27 | 2026-05-03
AD-03 | Filter Workload by Term or Module | As an Admin, I want to filter workload data by term or module, so that I can analyse staffing patterns more effectively. | high | 4 | • Verify that workload data can be filtered by term, module, or department. • Verify that filtered results update correctly. • Verify that clearing the filters restores the complete dataset. | 3 | Depends on AD-02. | 2026-04-28 | 2026-05-04
AD-04 | Detect Overloaded TAs | As an Admin, I want to detect overloaded TAs, so that I can identify unfair or excessive workload assignments. | very high | 4 | • Verify that the system flags TAs whose workload exceeds the configured threshold. • Verify that the admin can view the list of overloaded TAs. • Verify that the threshold used for overload checking can be configured by an authorised user. | 5 | Supports workload fairness checks. | 2026-04-29 | 2026-05-06
AD-05 | View Hiring Distribution | As an Admin, I want to view hiring distribution, so that I can check whether opportunities are allocated fairly among TAs. | high | 4 | • Verify that the admin can view how opportunities are distributed across TAs. • Verify that the view highlights both under-assigned and heavily assigned TAs. • Verify that the distribution data is consistent with the hiring records. | 5 | Supports allocation fairness analysis. | 2026-05-01 | 2026-05-07
AD-06 | View All Job Postings | As an Admin, I want to view all job postings, so that I can oversee recruitment activity across the whole system. | medium | 3 | • Verify that the admin can view all job postings created by module organisers. • Verify that each posting shows owner, module, deadline, and status. • Verify that the list includes both open and closed postings. | 3 | Supports oversight of recruitment activity. | 2026-04-13 | 2026-04-17
AD-07 | View Application Statistics | As an Admin, I want to view application statistics, so that I can evaluate overall recruitment performance. | medium | 4 | • Verify that the admin can view total applications, acceptances, and rejections. • Verify that the statistics are calculated from the current system data. • Verify that the displayed totals remain consistent across the reporting views. | 3 | Supports management reporting. | 2026-05-02 | 2026-05-08
AD-08 | Manage User Accounts | As an Admin, I want to manage user accounts, so that I can control access and maintain system integrity. | high | 5 | • Verify that the admin can activate, suspend, or deactivate user accounts. • Verify that suspended or deactivated users cannot log in. • Verify that account status changes are saved immediately. | 5 | Supports system governance. | 2026-05-11 | 2026-05-17
AD-09 | Generate Management Report | As an Admin, I want to generate management reports, so that I can support review and decision-making at school level. | low | 5 | • Verify that the admin can export management reports in a supported format. • Verify that exported reports match the data shown on screen. • Verify that generated files can be downloaded successfully. | 5 | Management-facing enhancement. | 2026-05-13 | 2026-05-20
AD-10 | View Audit Log | As an Admin, I want to view the audit log, so that I can trace important actions taken in the system. | very low | 5 | • Verify that the admin can view audit log entries for key system actions. • Verify that each log entry shows the action, user, and timestamp. • Verify that audit log entries are read-only. | 3 | Audit and traceability enhancement. | 2026-05-15 | 2026-05-22
AD-11 | Reset Admin Password | As an Admin, I want to reset my password using a secure recovery process, so that I can regain access if I forget it. | very high | 1 | • Admin can initiate password reset via email link. • System generates a time-limited reset token. • New password must meet complexity. • Password is updated and logged securely. | 3 | Should integrate with university email service. | 2026-05-15 | 2026-05-22
AD-12 | View Login Activity | As an Admin, I want to view login history and failed attempts, so that I can monitor system security. | high | 2 | • Admin can access a dashboard showing recent logins by role. • Failed login attempts are logged with timestamp and IP. • Ability to filter logs by date/role. | 5 | Useful for auditing and detecting suspicious activity. | 2026-05-11 | 2026-05-17
AD-13 | Export Workload Report | As an Admin, I want to export workload data to a CSV file, so that I can share it with other administrators or use it for offline analysis. | medium | 4 | • Verify that a button or link is available to export the current workload view (or all workload data). • Verify that the exported file is in CSV format and contains all relevant fields (TA name, modules, total hours, etc.). • Verify that special characters and line breaks are handled correctly in the export. | 3 | Depends on AD-02; useful for reporting | 2026-05-01 | 2026-05-07
AD-14 | Configure Workload Threshold | As an Admin, I want to configure the workload threshold (maximum allowed hours) for TAs, so that overload detection can be customised per semester. | high | 4 | • Verify that the admin can access a configuration page to set the threshold value. • Verify that the threshold is saved and used by the overload detection feature (AD-04). • Verify that only authorised admins can modify the threshold. | 3 | Supports flexible fairness rules | 2026-05-02 | 2026-05-08
AD-15 | View Workload History | As an Admin, I want to view historical workload data for each TA across past terms, so that I can analyse long-term allocation patterns. | low | 4 | • Verify that the admin can select a past term and see workload data as it was at that time (or aggregated). • Verify that the historical view includes the same metrics as the current view (modules, hours, status). • Verify that data is correctly archived or recomputed from historical records. | 5 | Requires storing snapshots or querying past assignments | 2026-05-11 | 2026-05-17
AD-16 | View Allocation Fairness Index | As an Admin, I want to see a fairness index (e.g., Gini coefficient or simple distribution chart) of TA workloads, so that I can quickly assess whether assignments are balanced. | low | 4 | • Verify that a visual representation (e.g., bar chart or pie chart) shows the distribution of workload among TAs. • Verify that a numeric fairness metric (if feasible) is displayed. • Verify that the view updates when filters (term/module) are applied. | 5 | May require statistical calculation; consider using simple percentages | 2026-05-07 | 2026-05-13

## Glossary
Term | Abbreviation | Definition
Teaching Assistant | TA | A student or staff member applying for or performing teaching assistant work.
Module Organiser | MO | The course owner or hiring manager who creates jobs and selects applicants.
Administrator | Admin | A system-level user who monitors fairness, workload, and governance.
Curriculum Vitae | CV | A document uploaded by a TA to present qualifications, experience, and skills.
Job Posting | j.p | A vacancy published by a module organiser for TA recruitment.
Application | APP. | A TA's submission for a specific job posting.
Shortlisted | s.l. | An intermediate application status showing the TA is still under consideration.
Accepted | acc | A final application status showing the TA has been selected for the role.
Rejected | rej | A final application status showing the TA has not been selected.
Workload | w.l. | The total number of assigned jobs, hours, or tasks allocated to a TA.

## Epics
Epic ID | Epic Name | Description | Stories Included
EP-01 | Access & Identity Management | Foundational access control for the three main roles in the system. | TA-01, TA-02, MO-01, AD-01,AD-11,AD-12,MO-11,TA-11,TA-12
EP-02 | TA Profile & Application Management | TA onboarding, profile creation, CV handling, job discovery, and application tracking. | TA-03, TA-04, TA-05, TA-06, TA-07, TA-08, TA-09, TA-10
EP-03 | Job Posting Lifecycle | Creation, publication, maintenance, and closure of job postings by module organisers. | MO-02, MO-03, MO-04, MO-05, MO-12, MO-13, MO-14, MO-15
EP-04 | Candidate Screening & Selection | Review, filtering, shortlisting, and final decision-making for applicants. | MO-06, MO-07, MO-08, MO-09, MO-10,MO-16,MO-17,MO-18,MO-19
EP-05 | Workload Monitoring & Fairness | Admin monitoring of workload, allocation fairness, and recruitment statistics. | AD-02, AD-03, AD-04, AD-05, AD-06, AD-07,AD-11,AD-12, AD-13, AD-14, AD-15, AD-16, AD-17
EP-06 | Governance, Reporting & Audit | Account management, reporting, and audit-trail capabilities for administrators. | AD-08, AD-09, AD-10